REFACTRON Detailed Execution Plan Research-Backed 8-Week MVP Shipping Plan v2.0 · Final · May 2026

📖 What This Document Is The locked execution plan for Refactron v2.0. Built on 33 years of academic research on behavior-preserving refactoring. Built on 10+ years of industry precedent from Meta, Google, Instagram, OpenRewrite. Every decision is grounded in cited research. Every week has a binary gate. If something is not in this document, it is not in the MVP.

# Part 1 — Research Foundation

## 1.1 The Academic Lineage

The intellectual core of Refactron — deterministic transformations that provably preserve behavior — has a 33-year academic lineage that the LLM-coding-tool market is ignoring.

### Opdyke 1992 — The Foundational Document

William F. Opdyke's PhD thesis at UIUC, "Refactoring Object-Oriented Frameworks," defined refactoring as behavior-preserving program transformation. Introduced the critical concept that every refactoring has preconditions that must be checked before application.

Defined seven properties: unique superclass, distinct class names, distinct member names, inherited member variables not redefined, compatible signatures. Proved most low-level refactorings are trivially behavior-preserving while a few have undecidable preconditions — for which conservative algorithms suffice.

💡 Why This Matters for Refactron Opdyke's thesis is the academic justification for Refactron's existence. Safe refactoring requires checking preconditions, not pattern-matching tokens. Refactron implements Opdyke's precondition framework for every transform.

### Key Academic Sources

| Author/Year | Source | Why It Matters |
| --- | --- | --- |
| Opdyke 1992 | UIUC PhD thesis | Defined behavior-preserving transformation. Preconditions framework. |
| Roberts 1999 | UIUC PhD thesis | Smalltalk Refactoring Browser. Practical preconditions automation. |
| Mens & Tourwé 2002 | Springer LNCS | Graph-transformation formalism for proving correctness. |
| Fowler 1999, 2018 | Addison-Wesley | Practitioner's catalog of named transformations. |
| Letouzey 2012 | ICSE Workshop | SQALE methodology for technical debt remediation cost. |
| Wang et al. 2018 | ICSE 2018 | Only 22% of refactored code covered by tests. |
| Mongiovi 2014 | Sci Comp Programming | Canonical impact analysis paper. |
| Brunsfeld 2018 | Strange Loop | Tree-sitter design rationale. |

## 1.2 Industry Precedents

The pattern Refactron is implementing has been validated at scale by every major engineering organization.

### Meta — jscodeshift

Created at Facebook in 2015. Used internally for thousands of React migrations. Built on recast (format-preserving) and ast-types. Parses with Babel/Babylon/Flow/TS.

Critical lesson: jscodeshift was abandoned by Meta in 2024. Issue #587 confirms no active maintainers. The 9-year gap between v0.x and v17.0.0 is significant.

There is a real market gap for a maintained, opinionated, safety-first successor.

### Google — ClangMR

ICSME 2013 paper combines Clang compiler framework with MapReduce to refactor Google's C++ codebase at scale. Google chose semantic, type-attributed transformation over text-based find/replace.

### Instagram — LibCST

Python's standard ast module is lossy (drops comments, parens, whitespace). LibCST is a Concrete Syntax Tree that preserves all formatting details while exposing AST-like semantics.

Ships with ConvertFormatStringCommand which converts .format() to f-strings — exactly one of Refactron's planned transforms. This is Refactron's reference implementation.

### OpenRewrite by Moderne

Gold-standard large-scale automated refactoring framework. Lossless Semantic Tree concept: type-attributed and format-preserving. 5,000+ community recipes. Recipes are deterministic programs.

### Semgrep autofix

AST-based autofix succeeds in 96.4% of Python test cases and 100.0% of JavaScript test cases. Lesson: deterministic AST refactoring at high accuracy is achievable if scope is tight.

## 1.3 The LLM Failure Data

The case for the no-LLM refactoring engine is built on hard numbers.

| Stat | Source | Implication |
| --- | --- | --- |
| 40% | NYU 2022 study of 1,692 Copilot programs (IEEE S&P) | Of Copilot programs contain exploitable security vulnerabilities |
| 92.45% | ACM AST 2024 paper on Copilot test generation | Of Copilot-generated tests are broken or empty without existing suite |
| 19.7% | USENIX Security 2024 (576k samples, 16 LLMs) | Of recommended packages are fabricated. Enables slopsquatting attacks. |
| 33% | Stripe Developer Coefficient 2018 | Of dev time spent on tech debt (17.3 of 41.1 hours/week) |
| 62% | Stack Overflow 2024 Survey | Of developers cite tech debt as #1 frustration |

## 1.4 Market Validation

📊 The Five Numbers That Make The Pitch Developers actively want to pay down debt but lack tools that let them do it safely. That gap is Refactron's wedge. Bad code costs $85 billion annually (Stripe). Tech debt has $3 trillion impact on global GDP over 10 years (Stripe). Improving code quality is #1 source of satisfaction (Stack Overflow 2024).

## 1.5 Competitive Landscape

| Tool | Approach | Verifies first? | Deterministic? | Multi-lang? |
| --- | --- | --- | --- | --- |
| Cursor, Copilot | LLM completion | No | No | Suggests only |
| SonarQube, CodeAnt | Static analysis | N/A reports | Yes | No autofix |
| jscodeshift | AST codemod | No | Yes | JS/TS, unmaintained |
| LibCST codemods | CST codemod | No | Yes | Python only |
| OpenRewrite | LST recipes | Build tests | Yes | Mostly Java |
| Semgrep autofix | Pattern+autofix | No | Yes 96-100% | Polyglot shallow |
| Evōk Labs | Det engine claim | Claimed | Claimed | Pre-product |
| Refactron | AST + 3-gate | YES | YES | Python + TS |

# Part 2 — Product Identity

## The One Sentence

Refactron finds legacy code and technical debt in production codebases, refactors it to modern solutions, and proves nothing broke before touching a single file.

## What Refactron Is Not

- Not a linter

- Not a formatter

- Not a prettifier

- Not an AI assistant

- Does not suggest. Does not flag. Refactors.

## The Four Step Pipeline

| # | Step | What It Does |
| --- | --- | --- |
| 01 | Deep Analysis | Scans full dependency graph. Detects legacy patterns, deprecated APIs, technical debt. SQALE-style remediation cost per finding. Read-only. |
| 02 | Refactoring Engine | Deterministic, rule-based AST transforms. No LLM. Same input → same output. 10 transforms at launch. ts-morph + LibCST. THE MOAT. |
| 03 | Verification Engine | Three gates before any write: syntax, imports, test suite. All must pass. If any fail, original is never touched. Atomic write. |
| 04 | Documentation Engine | ONLY step using LLM. Generates docstrings, comments, changelogs. Runs ONLY on already-verified refactors. LLM never touches code. |

# Part 3 — The Ten Refactor Transforms

Ten transforms at launch. No more. Each has documented preconditions per Opdyke's framework.

## Python Transforms

| Transform | Before | After |
| --- | --- | --- |
| callback_to_async_await | def fetch(url, callback): | async def fetch(url): |
| format_to_fstring | "Hello %s" % name | f"Hello {name}" |
| manual_typecheck_to_hints | if isinstance(x, int): | def f(x: int) -> bool: |
| deprecated_api | requests.get(url) | httpx.get(url) |
| class_to_dataclass | class User: def __init__ | @dataclass class User: |

## TypeScript Transforms

| Transform | Before | After |
| --- | --- | --- |
| var_to_const_let | var count = 0; | const count = 0; |
| promise_chains_to_async | fetch().then().catch() | try { await fetch() } |
| implicit_any | function process(data) {} | function process(data: T): R |
| commonjs_to_esm | const x = require("x") | import x from "x" |
| promise_constructor_to_async | new Promise((res) => {}) | async function fn() {} |

## Hardest Transform: callback_to_async_await

Preconditions:

- Callback called exactly once at end of all branches

- No other use of asyncio in conflict

- Function is not a generator

Implementation: LibCST Transformer that converts the callback pattern to async/await and rewrites all call sites with await. Start here so the rest feel easy.

# Part 4 — Architecture

## The Locked Contracts

Two files. Written Day 1. Frozen Day 2. Never change after that.

| File | Contents |
| --- | --- |
| src/contracts.ts | Analyzer, Refactorer, Verifier, Documenter interfaces. RefactorPlan, FileChange, VerificationResult. TransformId enum. |
| src/adapters/interface.ts | ILanguageAdapter — every method every adapter must implement. |

## Tech Stack Decisions

| Choice | Rationale | Source |
| --- | --- | --- |
| ts-morph | Wraps TS Compiler API with full type info. Maintained by David Sherret. | ts-morph.com |
| LibCST | Lossless CST. Preserves formatting. Includes ConvertFormatStringCommand. | Instagram |
| tree-sitter | Incremental, error-recovering, multi-language, robust on broken code. | Brunsfeld |
| write-file-atomic | Maintained by npm team. POSIX rename + Windows MoveFileExW. | npm/npm |
| pnpm workspace | Faster than npm, better monorepo support. | pnpm.io |
| tsup | esbuild-based, simple config. | egoist/tsup |
| Biome | Replaces ESLint + Prettier, unified, faster. | biomejs.dev |
| Vitest | Native TS, fast, vite-aligned. | vitest.dev |

# Part 5 — The 8-Week Build Plan

⚠️ The Inviolable Rule Each week ends with a binary gate. If you cannot tick it Friday EOD, you do not start the next week. You finish what you started or you cut scope. You do not pretend.

WEEK 1 Lock Contracts + Failing Test

### Goal: Define every interface. Write the one test the MVP is engineered to pass. Ship nothing else. Day 1 — Write the one-page PRD. Frozen. Tape it to the wall. Day 2 — Define four engine interfaces. No implementations. Contracts frozen after today. Day 3 — Build fixture repos. python-legacy-mini and ts-legacy-mini. ~10 files each. Passing test suite. Day 4 — Write golden.test.ts — the failing test that the entire MVP is engineered to pass. Day 5 — Repo skeleton. pnpm + tsup + Biome + Vitest. CI runs failing test (must fail). Day 6-7 — Decision memo. ts-morph vs babel/recast. LibCST vs RedBaron/parso. Gate: Exactly one e2e test fails. CI green-on-fail. Only contracts in src/.

WEEK 2 Verification Engine

### Goal: Build the 3-gate engine BEFORE building anything to verify. The moat is verified. Day 8 — Gate 1: Syntax. LibCST re-parse for Python. ts-morph diagnostics for TS. Day 9 — Gate 2: Import Integrity. Build dependency graph from proposed-new-content trees. Day 10 — Gate 3: Test Suite. Shadow tree copy + subprocess. Run baseline first. Cite Wang et al. 2018 — only 22% of refactored code is covered. Day 11 — Atomic write via write-file-atomic. BatchAtomicWriter for all-or-nothing. Day 12 — Unit + integration tests for all three gates. Day 13-14 — Buffer for gate work that will take longer than expected. Gate: Broken plan rejected at correct gate. Valid plan passes and atomic-writes.

WEEK 3 Deep Analysis Engine

### Goal: Scan codebase, build graphs, detect patterns, SQALE cost report. Read-only. Day 15 — File discovery + language detection. Respect .gitignore. Classify .py/.ts/.js/.tsx. Day 16 — Parsing pipeline. Tree-sitter fast first-pass. ts-morph/LibCST precise second pass. Day 17 — Python pattern detectors (5). One per planned transform. Day 18 — TypeScript pattern detectors (5). var, promise chains, implicit any, commonjs, promise ctor. Day 19 — Graph construction. Import graph + call graph. JSON export. Day 20-21 — SQALE cost report per Letouzey 2012. Pretty CLI output + JSON for CI. Gate: refactron analyze runs in <5s on fixtures. Detects every seeded pattern. Zero false negatives.

WEEK 4 Refactoring Engine — The Moat

### Goal: All 10 transforms with full preconditions. The week the moat is forged. Day 22 — Python #1: callback_to_async_await. Hardest. Start here. Day 23 — Python #2-3: format_to_fstring (ship LibCST's as-is) + manual_typecheck_to_hints. Day 24 — Python #4-5: deprecated_api (requests→httpx only) + class_to_dataclass. Day 25 — TS #6-7: var_to_const_let + promise_chains_to_async. Day 26 — TS #8-9: implicit_any + commonjs_to_esm. Day 27 — TS #10: promise_constructor_to_async. Hardest TS transform. Day 28 — Hardening: 10 positive + 5 negative + 3 edge fixtures per transform. ~180 tests total. Gate: Every transform passes full fixture suite. Negative fixtures rejected at precondition stage. E2E test from Week 1 passes.

WEEK 5 Language Adapters + Polish

### Goal: Unified output. JSON for CI. Dry-run. Diff preview. .refactronrc. Interactive mode. Day 29 — Unified LanguageAdapter interface. Clean up Week 3-4 organic growth. Day 30 — .refactronrc.json schema. Loaded via cosmiconfig. Day 31 — Diff preview with diff npm package + chalk. --dry-run shows changes without writing. Day 32 — Interactive review mode — y/n/q/? a la git add -p. Comby UX reference. Day 33 — JSON output mode for CI integration. Day 34-35 — Cross-platform polish. Test on macOS, Linux, Windows. Budget a day for Windows. Gate: All 3 platforms green on CI. Interactive mode works end-to-end. Config drives behavior.

WEEK 6 Documentation Engine (LLM, scoped)

### Goal: Step 4 — the ONLY LLM-touching component. Docs for already-verified refactors. Day 36 — LLMProvider interface. OpenAI + Anthropic + Ollama (local, default). Day 37 — Prompt templates: docstring, inline comment, CHANGELOG entry. Day 38 — Token-budget control. Chunk diffs at function boundaries. Secret redaction. Day 39 — Idempotency + caching. Hash (diff + prompt + model) → cache response. Day 40 — Failure modes. LLM down/garbage → fall back to "docs skipped, refactor succeeded." Day 41-42 — Integration tests with local Ollama. CI does not depend on paid APIs. Gate: Full pipeline runs with local LLM. LLM failure does not block refactor. LLM is non-blocking.

WEEK 7 CLI + Real-World Testing

### Goal: 5 real-world legacy codebases. Zero crashes. Fix every bug surfaced. Day 43 — CLI structure. analyze, run, document, init. Global flags. 3-line safety help. Day 44 — Gauntlet #1: your own production codebase. Triage findings. Day 45 — Gauntlet #2-3: two industry beta users. Watch them use it. Take notes only. Day 46 — Bug-fix day. Top 5 issues. Cut features causing bugs. Day 47 — Gauntlet #4-5. Different stacks (one Django, one Express). Day 48-49 — Performance pass. 10k/100k/500k LOC fixtures. Target <60s on 100k. Gate: 5 external devs ran Refactron end-to-end. Either completed successfully OR failed safely. Never wrote broken code.

WEEK 8 External Validation + Ship

### Goal: 3 of 5 validators say "I would use this." Publish to npm + PyPI. Show HN. Day 50 — Security audit. npm audit, pip-audit. Windows atomic-write. Subprocess sandboxing. Day 51 — Documentation site. Cite Opdyke, jscodeshift, LibCST, ClangMR in FAQ. Credibility lives here. Day 52 — README polish. The repo IS the landing page. Demo GIF via vhs from charm.sh. Day 53 — npm publish --dry-run. Verify package.json. Install on fresh Docker. Provenance. Day 54 — PyPI legacy wrapper. Detects Node, installs npm, shells out. Day 55 — Pre-write Show HN comment thread responses. Honest answers, no marketing. Day 56 — SHIP DAY. See Part 6 for launch playbook. Gate: npm install -g refactron returns 2.0.0. Show HN live. Founder answers every reply in 30 min for 12 hours.

# Part 6 — Shipping Day Execution

## Pre-Ship Checklist (Sunday Day 55 evening)

- npm whoami returns your account. 2FA on.

- npm publish --dry-run shows expected file list.

- pip install -e . works for wrapper.

- README final read-through on mobile (HN traffic skews mobile).

- Demo GIF under 5MB, under 30s, no audio.

- Discord/Slack/Twitter cleared for launch day.

- Phone fully charged. Charger nearby.

## Ship Day Timeline

| Time | Action |
| --- | --- |
| T-2h | Final smoke test on clean Docker container. npm install -g refactron from scratch. |
| T-1h | Publish. npm publish --provenance --access public. python -m build && twine upload. |
| T-0 | Post Show HN. Title: "Show HN: Refactron — Deterministic CLI that verifies refactors before writing" |
| T+0 | Tweet thread (8 tweets, demo GIF first). dev.to post. Lobste.rs. Reddit. Email beta users. |
| T+1h to T+12h | Answer every comment in 30 min. Never defend. Find agreeable kernel first. |

## Target Metrics

| Window | Target | Failure trigger |
| --- | --- | --- |
| Day 1 | 500 stars, 1k npm downloads, 50 HN comments, 5 issues | <200 stars → amplify on dev networks |
| Week 1 | 5k npm downloads, 1.5k stars, 1st external PR, 10 issues triaged | <2k downloads → re-test message |
| Month 1 | 20k downloads, 3k stars, 3 enterprise pilots, 2 community transforms | <1k downloads → positioning wrong |

# Part 7 — Risk Analysis

## Technical Risks

| # | Risk | Mitigation |
| --- | --- | --- |
| R1 | 10 transforms harder than estimated | Ship 6 rock-solid > 10 buggy. Wang et al.: one buggy transform poisons trust permanently. |
| R2 | Test gate non-deterministic (flaky tests) | Retry baseline 3x. Document. --skip-test-gate with red warning. Coverage stats per Wang. |
| R3 | ts-morph stale node bugs | Never hold node refs across mutations. Re-lookup via getSourceFile(path). |
| R4 | Atomic writes broken on Windows | write-file-atomic handles MoveFileExW. Test on Windows. If unfixable, Tier 2. |

## Market Risks

| # | Risk | Mitigation |
| --- | --- | --- |
| R5 | Evōk Labs ships first | Speed. Differentiation: actually ship transforms. MIT-licensed. Cite academic foundations. |
| R6 | Cursor/Copilot adds "verified mode" | Stay deeper. Cite NYU 40%, UTSA 19.7%, ACM 92.45% in every channel. |
| R7 | Mistaken for "yet another linter" | Lead with demo. ESLint tells. Refactron fixes AND proves. |

## Execution Risks

| # | Risk | Mitigation |
| --- | --- | --- |
| R8 | Solo-founder bandwidth | Weekend buffer in most weeks. Week 6 (LLM docs) easiest to cut. |
| R9 | Beta users go silent in Week 7 | Schedule calls in Week 6. Pre-commit. Offer attribution. |
| R10 | Show HN flops | Engage every comment. Re-post in 4 weeks if dies. Seed via dev.to, Lobste.rs, Reddit. |

# Part 8 — The Inviolable Rules

| # | Rule |
| --- | --- |
| 1 | contracts.ts locked Day 2. Cannot change after that. |
| 2 | No phase starts until previous gate passes. Binary check. |
| 3 | The refactoring engine NEVER uses LLM. This is the moat. |
| 4 | Verification runs before every write. Atomic write always. |
| 5 | Original file is never touched unless safe. Never. Not rolled back. |
| 6 | Self-analysis must pass before every release. Zero CRITICAL. |
| 7 | Test coverage above 80% before ship. |
| 8 | Documentation engine is the only LLM step. Everywhere else: deterministic. |
| 9 | 3 of 5 external validators must say "I would use this" before v2.0.0. |
| 10 | No new features added mid-build. Backlog everything. |

# Citations

## Academic Foundation

- Opdyke, W. F. (1992). "Refactoring Object-Oriented Frameworks." PhD thesis, UIUC.

- Roberts, D. (1999). "Practical Analysis for Refactoring." PhD thesis, UIUC.

- Mens, T. & Tourwé, T. (2002). "Formalising Behaviour Preserving Program Transformations." Springer LNCS.

- Fowler, M. (1999, 2018). Refactoring: Improving the Design of Existing Code. Addison-Wesley.

- Letouzey, J.-L. (2012). "The SQALE method for evaluating Technical Debt." ICSE Workshop on Managing Technical Debt.

- Wang, K. et al. (2018). "Towards Refactoring-Aware Regression Test Selection." ICSE 2018.

- Mongiovi, M. et al. (2014). "Making Refactoring Safer Through Impact Analysis." Science of Computer Programming 93.

- Brunsfeld, M. (2018). "Tree-sitter: a new parsing system for programming tools." Strange Loop 2018.

- AlOmar, E.A. et al. (2021). "On Preserving the Behavior in Software Refactoring: A Systematic Mapping Study." arXiv:2106.13900.

## Industry Sources

- Facebook/jscodeshift: github.com/facebook/jscodeshift

- Google ClangMR: research.google/pubs/large-scale-automated-refactoring-using-clangmr/

- Instagram LibCST: github.com/Instagram/LibCST

- Instawork engineering: engineering.instawork.com/refactoring-a-python-codebase-with-libcst

- OpenRewrite/Moderne: docs.openrewrite.org

- Semgrep autofix: semgrep.dev/blog/2022/autofixing-code-with-semgrep

- ts-morph: ts-morph.com, npmjs.com/package/ts-morph

- write-file-atomic: github.com/npm/write-file-atomic

## Market Validation

- Stripe & Harris Poll (2018). "The Developer Coefficient."

- Stack Overflow (2024). Developer Survey 2024.

- Pearce, H. et al. (2022). "Asleep at the Keyboard?" IEEE S&P 2022, arXiv:2108.09293.

- Spracklen, J. et al. (2024). "We Have a Package for You!" USENIX Security 2024, arXiv:2406.10279.

- El Haji, K. et al. (2024). "Using GitHub Copilot for Test Generation in Python." ACM/IEEE AST 2024, doi:10.1145/3644032.3644443.

- Liu, F. et al. (2024). "Beyond Functional Correctness: Exploring Hallucinations in LLM-Generated Code." arXiv:2404.00971.

The Product in One Sentence Every codebase has code nobody wants to touch. Refactron goes in, modernizes that legacy code, and proves nothing broke before changing a single file. Build. Verify. Ship. refactron.dev · npm install -g refactron · pip install refactron